## Main
| Today | Copy this doc and follow the link below for instructions. |  |  | 250.5 | 0 |  |  |  | 47 | 2 | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 4 | 3
| 2016-12-16 | http://bazald.com/eecs-494/burndown |  |  | Hours | Hours | Hours |  |  | Wed | Fri | Mon | Fri | Mon | Fri | Mon | Fri | Mon | Fri | Mon | Fri | Mon | Fri | Mon | Bug Statuses are used below in the bug area | Bug
# | Rank | Task | Assn | Assist | Est. | Rem. | Worked |  |  | 2016-10-26 | 2016-10-28 | 2016-10-31 | 2016-11-04 | 2016-11-07 | 2016-11-11 | 2016-11-14 | 2016-11-18 | 2016-11-21 | 2016-11-25 | 2016-11-28 | 2016-12-02 | 2016-12-05 | 2016-12-09 | 2016-12-12 | Detailed Information | Status
Task Assignments | [25 empty] | Reported
11 |  | General Tasks | [23 empty] | Can't Repro
7 | 1 | Set up the project and push to github | ALL |  | 0.5 | 0 |  |  | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Verify?
8 | 1 | Meet and plan a 0.1 | ALL |  | 1 | 0 |  |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Support for 4 players, NPC patient that can die (failure), 4 players must cooperate to save the patient (win), needs to be some obstical, some variation in tasks to save the patient, small tasks to complete to globally save the patient. | Fixed
9 | 1 | PLAY "OVERCOOKED" - THIS IS BASCIALLY WHAT WE WANTED TO MAKE | ALL |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Deferred
15 | 1 | Other game research | ALL |  | 1 | 0 |  |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | 1 | Refine vision for game | ALL |  | 1 | 0 |  |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 2 | Research other games for Research and analysis (1 - 2 games per person) | ALL |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 2 | Write Research and Analysis document | ALL |  | 6 | 0 |  |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Morgan: Lovers in a Dangerous Space Time Eliana: Tiny Brains Alex: Move of Die Ben: I Expect you to die To Be decided: Overcooked and one other game (recipe game?)
16 | 1 | fill out burn down chart, divide responsibilites | ALL |  | 0.5 | 0 |  |  | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20
21
22 |  | Core Mechanics (for prototype)
23 | 1 | Support for 4 conrollers | BL |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1-4 controllers are detected
24 | 1 | Controls for 4 controllers | BL |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | 1 | Split screen | ME |  | 2 | 0 | 1.5 |  | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | 1 | Patient (Placeholder) | AC |  | 0.5 | 0 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | 1 | Fail state when patinet is neglected (simple patient vitals) | ME |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | 1 | 4 tools that can interact with 4 things in the environment | AC |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | You should be able to pick up tools, carry them somewhere else, interact with something particular in the environment (change its state) and drop the tool somewhere else.
29 | 1 | Lay out basic level (some simple surgery room) | EA |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | 1 | 4 doctors | AC |  | 0.5 | 0 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | 1 | Win State | BL |  | 0.5 | 0 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | 1 | What are the 4 things in the environment | ALL |  | 6 | 0 |  |  | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Hours are inflated because everyone will be workng on this
30 | 1 | Countdown (anethetics) --> initiates fail state | ME |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | 1 | Events signaling to players that they need to do an action (interacting with an object in the environment) | EA |  | 2 | 0 | 3 |  | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | 1 | Camera Setup | ME |  | 0.5 | 0 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | 1 | Set up function stubs (get project ready to be worked on in parallel) | ALL |  | 6 | 0 |  |  | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Hours are inflated because everyone will be working on this
31
32
33
34
35
36 |  | Core Mechanics (for GoldSpike)
37 | 2 | Scalpel Model and Class | EA | BL | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Model / Class (tool)
38 | 2 | Forceps Model and Class | EA |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | 2 | Sutchers Model and Class | EA | BL | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | 2 | Gauze Model and Class | EA |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | 1 | Anesthetic Machine Functionality | AC |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | 1 | Washing Station Functionality | AC |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | 1 | Round out Doctor Movement | AC |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | 1 | Sutchers interact with patient | BL |  | 6 | 0 |  |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | 1 | Making Patient Body Interactive/Responsive to tools | BL |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | 1 | Scalpel interacts with patient | BL |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | 1 | Forcepts interact with patient | BL |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 1 | Event System Works with tools and patient. | ME |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | 1 | Recipes for event system | ME | ALL | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | 1 | Gauze interacts with patient | BL |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | 2 | Ui for recipies and events | ME | EA | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
52 | 2 | Anesthetic Machine Model | EA | BL | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | 2 | Washing Station Model | EA | BL | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | 2 | Refine Camera / perspective and only show tools and patient on patient camera | ALL |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | 1 | Heart rate more dynamic (changes speed and lets player know when the patinet is about to die) | EA | ME | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | 4 | Defibulator Model | BL |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
57 | 3 | Defibulator Functionality (Add more Functionality) **specify?? | EA |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
58 | 1 | Container dispensing container / system / method for Capsules | AC |  | 2.5 | 0 |  |  | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
59
36
61
62
63
64 |  | Backlog
65 | 4 | Fire Aesthetics | BL |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0
66 | 3 | Fire Logic / Interaction | ME |  | 2 | 0 | 3 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67 | 3 | Moveable Gurney | EA |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 | 4 | Bear Model / class | EA |  | 5 | 0 |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0
69 | 3 | Bear AI | EA |  | 6 | 0 |  |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | 3 | Bear Interacting with players | EA |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
55 | 5 | Refined player guidence (AI or some kind of tutoiral) | ME |  | 5 | 0 | 2 |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | 3 | alpha planning | ALL |  | 6 | 0 |  |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | 4 | Pull out stick from body | ALL |  | 2 | 0 | Remvoed |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
58 | 4 | Pull out stick from body aesthetics | ALL |  | 2 | 0 | Removed |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
59 | 4 | Raccoons AI? --> stealing tools | BL |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | 4 | Raccoons Aesthetics | EA |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0
77 | 3 | Pond (for collecting water in buckets) | AC |  | 1.5 | 0 |  |  | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 | 0 | 0 | 0
78 | 3 | Water bucket tool | AC | EA | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | 3 | Add Dirty Hands Mechanic | AC | AC | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | 3 | Water Bucket Model | EA | BL | 0.5 | 0 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | 3 | Highlight interactive element nearest to doctor | AC |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
82 | 4 | Prevent interactions with elements which are in range, but not in front of doctor | AC |  | 0.5 | 0 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0
| 2 | HeartBeat | ME |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | 1 | Fix highlighting for complex objects | AC |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | 1 | Add special highlighting to current necessery tool | AC |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
85 | 1 | Fx doctor colliders | AC |  | 0.25 | 0 |  |  | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 |  | Make/Update Doctor Prefab | AC |  | 0.25 | 0 |  |  | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 |  | Clean up project (remove defunct scripts / unused prefabs) | AC |  | 0.25 | 0 |  |  | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 |  | Aesthetics
89 |  | Patient body model Refinement | BL | EA | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
90 |  | Refine Camera / perspective and only show tools and patient on patient camera
91 |  | Better wash Hands Meter | EA |  | 0.25 | 0 |  |  | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0
92 |  | Fix Movement Bug | AC |  | 0.5 | 0 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Bascially fixed. Setting the mass of the doctors to ~0 means that any collision with another object will not generate that much force between them. With very little force, there is very little resulting change in volocity. You can still see the doctor move slightly when replicating this bug, but it is far better than it was before.
93 | 1 | Events for Bear, Fire, and Raccons | ME |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | 1 | Force canvas above doctor's head to "look at" the screen at all times. | AC |  | 0.75 | 0 |  |  | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | 1 | Graphics for Tools notifications | ME |  | 3 | 0 | 3 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
96 | 1 | Graphics for Environment event notifications | ME |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
97 | 1 | Graphics for button events | ME |  | 3 | 0 | 2 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | Attach graphics to event system | ME |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
98 | 1 | Set up button press graphics with Objects | ME |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
99 |  | Prevent tools from moving off surgery screen | AC |  | 1.5 | 0 |  |  | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
100 |  | Fix oringal tool matieral getting overwritten | AC
101 |  | Restrict players from leaving the area | BL |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
102 |  | Make arena bigger | BL |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
103 | 1 | New Tool Spawning when raccoons steal them | BL |  | 0.5 | 0 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
104 | 1 | Animal Spawning | BL |  | 0.5 | 0 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
105 | 1 | Icons over interactables | ME |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | Play testing Script | ALL |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0
| 1 | Put it together for alpha | ALL |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0
| 1 | Fail / Success | AC |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | Tutorial Slides | AC |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | Defibulator Cooldown
111 | 1 | Animate Heart Rate Monitor | ME |  | 6 | 0 |  |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0
112 | 1 | Incorporate Heart Rate Monitor | ME |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
113 | 1 | Notifications for Bear and Wash hands | ME |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
114 | 1 | Make UI not screen dependent | ME |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
115 | 1 | Tutorial planning | ALL |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
116 | 1 | Tutorial Slides based on completed tutorial actions? | ME | BL | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
117 | 1 | Connect Sounds | EA |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
118 | 1 | Find Sounds | EA |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
119 | 1 | Tutorial Implementation | ALL |  | 8 | 0 |  |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
120 | 3 | Winning Screen | BL | EA | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
121 | 3 | Screen Transitions | BL |  | 0.5 | 0 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0
122 | 3 | Player Start Screen | BL | EA | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
123 | 1 | Refined Dash (Particle Effects, change in speed) | BL |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
124 | 1 | Refined Bear (Faster, further away, obvious when it is detered) | EA |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
125 | 2 | Graphics for tutorial slides | ME |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0
| 1 | Tutorial Implementation | ME |  | 4 |  | 8 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0
128 | 3 | Some kind of cut scene, or something to explain to the player why they are in the woods | BL |  | 5 | 0 |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
129 | 1 | Progress indicator for surgery | ME |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
130 | 3 | Adding all around juiciness | ALL |  | 7 | 0 |  |  | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0
131 | 4 | Balance spawns, rates, etc. | ALL |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
132 | 3 | Lay out final level design (and tools on table) | ALL |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
133
134
135
136
137
138
139
140 | 5 | Prepare for Gamma Submission | ALL |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0
141 | 5 | Prepare and final debug and testing for Showcase | ALL |  | 8 | 0 |  |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
142
143
Bugs to be Fixed!!! | [24 empty] | Fix Description (if unusual or useful to later generations) | Status
107 | 1 | Fix floating tools off screen | AC |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fixed
108 |  | make hands or something so tools don't float around in the world just on camera | [23 empty] | Fixed
109 |  | Fix occassional sliding | AC |  | 0.25 | 0 |  |  | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fixed
110 | 2 | Does fire generate multiple times in the same place? | ME |  | 0.5 | 0 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 |  | Fixed
149 | 1 | Heart rate / Patient death last two states don't work right | ME |  | 0.5 | 0 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 |  | Fixed
150 | 1 | Patient dies sometimes randomly (maybe when anesthetic machine runs out --> but not seemingly deterministically) | ME |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | Fixed
151 | 1 | Can get stuck in fire, should you be able to walk through fire? | ME |  | 0.5 | 0 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 |  | Fixed
152 | 1 | Cant scare away bear | EA |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | Fixed
153 | 1 | Interactables too large sphere (causes the wrong things to be activted / too far away and bear not to work) | AC |  | 0.5 | 0 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 |  | Fixed
154 | [25 empty] | Reported
155 | [25 empty] | Reported
156 | [25 empty] | Reported
157 | [25 empty] | Reported
158 | [25 empty] | Reported
159 | [25 empty] | Reported
160 | [25 empty] | Reported
161 | [25 empty] | Reported
162 | [25 empty] | Reported
163 | [25 empty] | Reported
164 | [25 empty] | Reported
165 | [25 empty] | Reported
166 | [25 empty] | Reported
167 | [25 empty] | Reported
168 | [25 empty] | Reported
169 | [25 empty] | Reported
170 | [25 empty] | Reported
171 | [25 empty] | Reported
172 | [25 empty] | Reported
173 | [25 empty] | Reported
174 | [25 empty] | Reported
175 | [25 empty] | Reported
176 | [25 empty] | Reported
177 | [25 empty] | Reported
178 | [25 empty] | Reported
179 | [25 empty] | Reported
180 | [25 empty] | Reported
181 | [25 empty] | Reported
182 | [25 empty] | Reported
183 | [25 empty] | Reported
184 | [25 empty] | Reported
185 | [25 empty] | Reported
186 | [25 empty] | Reported
187 | [25 empty] | Reported
188 | [25 empty] | Reported
189 | [25 empty] | Reported
190 | [25 empty] | Reported
191 | [25 empty] | Reported
192 | [25 empty] | Reported
193 | [25 empty] | Reported
194 | [25 empty] | Reported
195 | [25 empty] | Reported
196 | [25 empty] | Reported
197 | [25 empty] | Reported
198 | [25 empty] | Reported
199 | [25 empty] | Reported
200 | [25 empty] | Reported
201 | [25 empty] | Reported
202 | [25 empty] | Reported
203 | [25 empty] | Reported
204 | [25 empty] | Reported
205 | [25 empty] | Reported
206 | [25 empty] | Reported
207
208
Interpreted Data
210 |  | Days | [6 empty] | 47 | 47 | 45 | 42 | 38 | 35 | 31 | 28 | 24 | 21 | 17 | 14 | 10 | 7 | 3 | 0
211 |  | Optimum | [5 empty] | Line | 250.5 | 250.5 | 239.8404 | 223.8511 | 202.5319 | 186.5426 | 165.2234 | 149.234 | 127.9149 | 111.9255 | 90.6064 | 74.617 | 53.2979 | 37.3085 | 15.9894 | 0
212
213 |  | Sum | [6 empty] | 250.5 | 250.5 | 250.5 | 250.5 | 250.5 | 250.5 | 250.5 | 250.5 | 250.5 | 250.5 | 250.5 | 250.5 | 250.5 | 250.5 | 250.5 | 250.5
214 |  | Rank (and not reduced to 0 after today)
215 |  | Rank 1 - The MOST important | 1 | [5 empty] | 139 | 139 | 138.5 | 135 | 118.5 | 112 | 106 | 72.75 | 68.25 | 64.5 | 43.5 | 35.5 | 27 | 20 | 15 | 0
216 |  |  | 2 | [5 empty] | 31.5 | 31.5 | 31.5 | 31.5 | 31.5 | 31.5 | 27.5 | 7.5 | 7.5 | 7.5 | 3.5 | 3 | 3 | 3 | 0 | 0
217 |  |  | 3 | [5 empty] | 39.5 | 39.5 | 39.5 | 39.5 | 39.5 | 39.5 | 39.5 | 39.5 | 21 | 21 | 20 | 19 | 17.5 | 17.5 | 17 | 0
218 |  |  | 4 | [5 empty] | 24.5 | 24.5 | 24.5 | 24.5 | 24.5 | 24.5 | 24.5 | 24.5 | 24.5 | 21.5 | 19.5 | 10.5 | 7 | 3 | 3 | 0
219 |  | Rank 5 - The LEAST important | 5 | [5 empty] | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 11 | 11 | 11 | 11 | 11 | 8 | 8 | 0
220
221 |  | Assigned (Replace these with your team members!)
222 |  | Morgan | ME |  |  |  |  | ME | 66 | 66 | 66 | 66 | 62.5 | 60.5 | 60.5 | 51.5 | 42.5 | 42.5 | 23.5 | 21 | 12.5 | 8 | 3 | 0
223 |  | Alex | AC |  |  |  |  | AC | 33.75 | 33.75 | 33.75 | 33.75 | 31.25 | 29.75 | 29.75 | 18.75 | 12.75 | 9 | 3 | 3 | 1 | 0 | 0 | 0
224 |  | Eliana A | EA |  |  |  |  | EA | 41.75 | 41.75 | 41.75 | 41.75 | 41.75 | 38.75 | 38.75 | 24.75 | 17.25 | 17.25 | 16.25 | 10.25 | 7.25 | 5.25 | 4.25 | 0
225 |  | Ben L | BL |  |  |  |  | BL | 40 | 40 | 40 | 40 | 36.5 | 36.5 | 36.5 | 23.5 | 23.5 | 20.5 | 17.5 | 13.5 | 11.5 | 11.5 | 9 | 0
226 |  | All | ALL |  |  |  |  | ALL | 75 | 75 | 74.5 | 71 | 64 | 64 | 54 | 47 | 41 | 41 | 41 | 35 | 35 | 28 | 27 | 0
227 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
228 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
229 | [7 empty] | Unassigned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
230 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
231 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
232 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233
234
235 | [7 empty] | DateLine | 250.5 | 250.5 | 250.5 | 250.5 | 250.5 | 250.5 | 250.5 | 250.5 | 250.5 | 250.5 | 250.5 | 250.5 | 250.5 | 250.5 | 250.5 | 250.5
236

## Daily Scrum
Producer | 2016-12-16 |  | Team Members
Approved | Dates |  | Morgan | Alex | Eliana A | Ben L | All
| 2016-10-26 | Wed | PROJECT NOT STARTED YET | PROJECT NOT STARTED YET | PROJECT NOT STARTED YET | PROJECT NOT STARTED YET | PROJECT NOT STARTED YET
| 2016-10-27 | Thu | PROJECT NOT STARTED YET | PROJECT NOT STARTED YET | PROJECT NOT STARTED YET | PROJECT NOT STARTED YET | PROJECT NOT STARTED YET
| 2016-10-28 | Fri | Done: Met and planned the mechanics of the game Next: Meet with team, to refine game ideas Help: — | Done: Met and planned the mechanics of the game Next: Meet with team, to refine game ideas Help: — | Done: Met and planned the mechanics of the game Next: Meet with team, to refine game ideas Help: — | Done: Met and planned the mechanics of the game Next: Meet with team, to refine game ideas Help: — | Done: Met and planned the mechanics of the game Next: Find similar games, play them, and refine vision of game Help: —
| 2016-10-29 | Sat | Done: Met with team to refine game ideas Next: Continue Planning / refining game based on in-class advice Help: — | Done: Met with team to refine game ideas Next: Continue Planning / refining game based on in-class advice Help: — | Done: Met with team to refine game ideas Next: Continue Planning / refining game based on in-class advice Help: — | Done: Met with team to refine game ideas Next: Continue Planning / refining game based on in-class advice Help: — | Done: Organized notes on similar games, and refined vision for our game Next: Continue Planning / refining game Help: —
| 2016-10-30 | Sun | NA | NA | NA | NA | NA
| 2016-10-31 | Mon | NA | NA | NA | NA | NA
| 2016-11-01 | Tue | Done: Set up burndown chart, played Overcooked Next: Prepare the project to be worked on seperatly Help: — | Done: Set up burndown chart, played Overcooked Next: Prepare the project to be worked on seperatly Help: — | Done: Set up burndown chart, played Overcooked Next: Prepare the project to be worked on seperatly Help: — | Done: Set up burndown chart, played Overcooked Next: Prepare the project to be worked on seperatly Help: — | Done: Set up burndown chart, played Overcooked, and decided what we wanted to include in our game, what we wanted our game to add, and what we didn't want in our game Next: Plan what we need to see in our Prototype, add these to the burndown chart, and start working seperatly Help: —
| 2016-11-02 | Wed | Done: Set up API to enable parallel work between members Next: Camera Setup and SplitScreen Help: — | Done: Set up API to enable parallel work between members Next: Patient Placeholders and 4 doctors Help: — | Done: Set up API to enable parallel work between members Next: Layout basic level Help: — | Done: Set up API to enable parallel work between members Next: Controller Support Help: — | Done: Decided what we wanted to see in our Prototype, and set up a skeleton API for thouse features / divided burndown tasks Next: Come together to make the prototype deliverable Help: —
| 2016-11-03 | Thu | NA | NA | NA | NA | NA
| 2016-11-04 | Fri | Done: Set up Camera and Split Screen Next: Patient Vitals Help: — | NA | NA | NA | NA
| 2016-11-05 | Sat | NA | NA | Done: Next: Work on patient interaction with event system | NA | NA
| 2016-11-06 | Sun | Done: Patient Vitals and Fial State Next: Wait for advice during prototype deliverable and refine prject from there Help: — | Done: Doctors can use tools Next: Advice time. | Done: Patient Vitals Trigger events in state Next: Feedback from deliverable Help: — | Done: Controller support for up to four players. Buttons are set. A to pickup. X to interact. Win state in. Game controller skelly. Next: iterate game controls | Done: Integrated everyones code Next: Plan between now and the gold spike Help: --
| 2016-11-07 | Mon | NA | NA | NA | NA | Done: Planed between now and the goldspike Next: Play games / game research Help: NA
| 2016-11-08 | Tue | NA | NA | NA | NA | NA
| 2016-11-09 | Wed | NA | NA | NA | NA | NA
| 2016-11-10 | Thu | Done: Research for research and Analysis Document Next: Write Research and Analysis Help: -- | Done: Played the games! Next: Wrate about the games! Help: -- | Done: Research for research and Analysis Document Next: Write Research and Analysis Help: -- | Done: Next: Help: -- | Done: Game research, talked about how they would effect our game Next: Come together and make game deliverable for GoldSpike Help: NA
| 2016-11-11 | Fri | Done: Research and Analysis Contribution Next: Implement Event System Help: -- | Done: Wrote reseradch and analysis Next: fire colliders Help: -- | Done: Research and Analysis Contribution Next: Create all models for game. Make classes Help: -- | Done: controller input Next: Help: -- | NA
| 2016-11-12 | Sat | Done: Event System Works with all tools and critical events Next: Heart rate better Help: -- | Done: Fixed fire colliders Next: New tools spawn with event sytem Help: -- | Done: Created scalpel, suture Next: All other models Help: -- | Done: doctor models Next: Help: -- | NA
| 2016-11-13 | Sun | Done: Heat rate better, and simple UI for displaying events Next: Prepare Project for Goldspike deliverable Help: -- | Done: Fixed tools and treec colliders to prevent escaping Next: Prepare Project for Goldspike deliverable Help: -- | Done: Created a new animation for suturing, helped out members with other tasks Next: All other models Help: Do we need it? | Done: Next: Help: -- | Done: Put code together / final touches for GoldSpike as a group Next: Plan What we want for the aplha Help: --
| 2016-11-14 | Mon | NA |  | Done: Turned in Next: Feedback for class Help: -- |  | NA
| 2016-11-15 | Tue | NA |  | NA |  | NA
| 2016-11-16 | Wed | Done: Heart Beat has sound Next: Work on fire Help: -- | Done: Improve water bucket graphics Next: fix bug with defibulator Help: -- | Done: Navmesh for bear Started bear model Next: Finish bear Help:-- | Done: Next: Help: -- | Done: Planed what we wanted for the alpha Next: -- Help: --
| 2016-11-17 | Thu | Done: Made fire prefabs and generable Next: Make graphics for notifications Help: -- | Done: Worked with Morgan on fire Next: Create test scene Help: -- | Done: still working on bear model, started code for bucket Next: Finish bear Help:-- | Done: Next: Help: -- | NA
| 2016-11-18 | Fri | Done: Started Graphics for Notification System Next: Finish Graphics for Notification System Help: -- | Done: tested new tools and water events Next: Help: -- | Done :Racooon models. Next: Finish bear, finish models. Help:-- | Done: Next: Help: -- | NA
| 2016-11-19 | Sat | Done: Finished Graphics for Notification System Next: Graphics for buttons hints Help: -- |  | Done : Made water bucket Next: Finish bear, finish models. Help:-- | Done: Next: Help: -- | NA
| 2016-11-20 | Sun | Done: Graphics for Buttons / hints Next: Connect Graphics to Event system Help: -- |  | Done :Racooon models. Next: Finish bear, finish models. Help:-- | Done: Next: Help: -- | NA
| 2016-11-21 | Mon | NA |  | NA |  | NA
| 2016-11-22 | Tue | NA |  | NA |  | NA
| 2016-11-23 | Wed | NA |  | NA |  | NA
| 2016-11-24 | Thu | NA |  | NA |  | NA
| 2016-11-25 | Fri | NA |  | NA |  | NA
| 2016-11-26 | Sat | Done: Basic Debugging Next: Connect Graphis to event system Help: -- |  | Done : Racooon models. Bear models Next: Finish bear, finish models. Help:-- | Done: Next: Help: -- | NA
| 2016-11-27 | Sun | Done: Connected Graphics to event system and put together code with group Next: Help: -- |  | Done: Finished bear (bear was hard to get right) Next: Finish bear interaction with people Help:-- | Done: Next: Help: -- | Done: Put together code for alpha deliverable and play testing script Next: Playtesting, and what do we need for the beta? Help: --
| 2016-11-28 | Mon | NA |  | Done: Finished setting up for turn in Next: get to work on the next deliverable Help:-- | Done: Next: Help: -- | Done: Planned what we wanted to see for the Beta Next: Put code together for Beta Help: --
| 2016-11-29 | Tue | NA |  | Done: Bear refinement part 1 Next: listen to feedback about game. Bear doesn't show up properly fix that. Help:-- | Done: Next: Help: -- | NA
| 2016-11-30 | Wed | Done: Created animation for Heart rate Monitor Next: Incorporate Heart Rate Monitor animation in code Help: -- |  | Done: Created animation for near death Next: more fixing based on feedback Help: -- | Done: Next: Help: -- | NA
| 2016-12-01 | Thu | Done: Created wash-hands notification Next: Incorporate Heart Rate monitor animation in code Help: -- |  | Done: made bear interact with dash Next: fix bugs Help: -- | Done: Next: Help: -- | NA
| 2016-12-02 | Fri | Done: Incorporated Heart Rate Monitor Animation in code Next: Refine button guidence over interactables and wash hands notification Help: -- |  | Done: refining bear in tutorial Next: finish music and sounds Help: -- | Done: Next: Help: -- | NA
| 2016-12-03 | Sat | Done: Refined button guidence over interactables and wash hand notification Next: Make UI not screen dependent and put code together for Beta Help: -- |  | Done: NA Next: Help: -- | Done: Next: Help: -- | NA
| 2016-12-04 | Sun | Done: Put code together for Beta and Made UI not screen dependent Next: Run Playtests for partner group Help: -- |  | Done: putting stuff together Next: Help: -- | Done: Tutorial scene skeleton Next: Help: -- | Done: Put code together for Beta Next: Playtesting implementation Help: --
| 2016-12-05 | Mon | NA |  | Done: Putting everything together for tutorial Next: Help: -- | Done: Next: Help: -- | Done: Playtesting Implementation Next: Put together playtest data for partner team Help: --
| 2016-12-06 | Tue | NA |  | Done: FIxing tutorial realted stuff with everyone Next: Bear in tutorial Help: -- | Done: Next: Help: -- | Done: Put together playtest data for partner team Next: Prepare for the design expo - go to the design expo Help: --
| 2016-12-07 | Wed | NA |  | Done: Bear in tutorial Video stuff Next: make script for video Help: -- | Done: Next: Help: -- | NA
| 2016-12-08 | Thu | NA |  | Done: Help with bugs. Next: record Help: -- | Done: Next: Help: -- | Done: Design Expo Next: Refine our ideas for a tutorial level Help: --
| 2016-12-09 | Fri | Done: Tutorial Graphics Next: Tutorial Slides Help: -- |  | Done: Next: Help: -- | Done: tutorial surgeries Next: surgery bug fixes Help: -- | Done: Next: Help: --
| 2016-12-10 | Sat | Done: Tutorial Slides Next: Tutorial Event System Help: -- |  | Done: fixed bugs pertaining to tutorial events Next: video Help: -- | Done: Next: Help: -- | Done: Next: Help: --
| 2016-12-11 | Sun | Done: Tutoiral Event System Next: Tutorial Tooltips Help: -- |  | Done: made video and audio Next: finish video Help: -- | Done: Next: balancing/bug fixing Help: -- | Done: Put game together for Gamma Next: Plan last additions to game (refinements) Help: --
| 2016-12-12 | Mon | NA |  | NA too many papers and exams | Done: Next: balancing/bug fixing Help: -- | Done: Planned last additions to game and refinements Next: Last-minute playtests Help: --
| 2016-12-13 | Tue | Done: Tutorial Tooltips Next: Fully Integrate Tutorial Help: -- |  | NA blah see above | Done: Next: Help: -- | Done: Last-minute playtests Next: Balence game, get ready for showcase Help: --
| 2016-12-14 | Wed | Done: Fully Integrate Tutorial Next: Surgery Progess Indicator Help: -- |  | Done: Help out with tutorial refinement and aesthetics. Next: moar refine!!! Help: I still have so much work to do :C | Done: win/lose scenes Next: balancing/bug fixing Help: -- | Done: Next: Help: --
| 2016-12-15 | Thu | Done: Surgery Progress Indicator Next: Refine game for showcase Help: -- |  | Done: Bug fixing Next: refinment Help: I hate everything :C | Done: last minute bug fixes Next: Help: -- | Done: Balanced game, put everything together, ready for showcase Next: Justiciation Document Help: --