## Main
| Today | Copy this doc and follow the link below for instructions. |  |  | 189 | 27 |  |  |  | 47 | 2 | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 4 | 3
| 2016-12-05 | http://bazald.com/eecs-494/burndown |  |  | Hours | Hours | Hours |  |  | Wed | Fri | Mon | Fri | Mon | Fri | Mon | Fri | Mon | Fri | Mon | Fri | Mon | Fri | Mon | Bug Statuses are used below in the bug area | Bug
# | Rank | Task | Assn | Assist | Est. | Rem. | Worked |  |  | 2016-10-26 | 2016-10-28 | 2016-10-31 | 2016-11-04 | 2016-11-07 | 2016-11-11 | 2016-11-14 | 2016-11-18 | 2016-11-21 | 2016-11-25 | 2016-11-28 | 2016-12-02 | 2016-12-05 | 2016-12-09 | 2016-12-12 | Detailed Information | Status
Task Assignments | [25 empty] | Reported
11 |  | General Tasks | [23 empty] | Can't Repro
7 | 1 | Set up the project and push to github | ALL |  | 0.5 | 0 |  |  | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Verify?
8 | 1 | Meet and plan a 0.1 | ALL |  | 1 | 0 |  |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Support for 4 players, NPC patient that can die (failure), 4 players must cooperate to save the patient (win), needs to be some obstical, some variation in tasks to save the patient, small tasks to complete to globally save the patient. | Fixed
9 | 1 | PLAY "OVERCOOKED" - THIS IS BASCIALLY WHAT WE WANTED TO MAKE | ALL |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Deferred
15 | 1 | Other game research | ALL |  | 1 | 0 |  |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | 1 | Refine vision for game | ALL |  | 1 | 0 |  |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 2 | Research other games for Research and analysis (1 - 2 games per person) | ALL |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 2 | Write Research and Analysis document | ALL |  | 6 | 0 |  |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Morgan: Lovers in a Dangerous Space Time Eliana: Tiny Brains Alex: Move of Die Ben: I Expect you to die To Be decided: Overcooked and one other game (recipe game?)
16 | 1 | fill out burn down chart, divide responsibilites | ALL |  | 0.5 | 0 |  |  | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20
21
22 |  | Core Mechanics (for prototype)
23 | 1 | Support for 4 conrollers | BL |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1-4 controllers are detected
24 | 1 | Controls for 4 controllers | BL |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | 1 | Split screen | ME |  | 2 | 0 | 1.5 |  | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | 1 | Patient (Placeholder) | AC |  | 0.5 | 0 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | 1 | Fail state when patinet is neglected (simple patient vitals) | ME |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | 1 | 4 tools that can interact with 4 things in the environment | AC |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | You should be able to pick up tools, carry them somewhere else, interact with something particular in the environment (change its state) and drop the tool somewhere else.
29 | 1 | Lay out basic level (some simple surgery room) | EA |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | 1 | 4 doctors | AC |  | 0.5 | 0 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | 1 | Win State | BL |  | 0.5 | 0 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | 1 | What are the 4 things in the environment | ALL |  | 6 | 0 |  |  | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Hours are inflated because everyone will be workng on this
30 | 1 | Countdown (anethetics) --> initiates fail state | ME |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | 1 | Events signaling to players that they need to do an action (interacting with an object in the environment) | EA |  | 2 | 0 | 3 |  | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | 1 | Camera Setup | ME |  | 0.5 | 0 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | 1 | Set up function stubs (get project ready to be worked on in parallel) | ALL |  | 6 | 0 |  |  | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Hours are inflated because everyone will be working on this
31
32
33
34
35
36 |  | Core Mechanics (for GoldSpike)
37 | 2 | Scalpel Model and Class | EA |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Model / Class (tool)
38 | 2 | Forceps Model and Class | EA |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | 2 | Sutchers Model and Class | EA |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | 2 | Gauze Model and Class | EA |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | 1 | Anesthetic Machine Functionality | AC |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | 1 | Washing Station Functionality | AC |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | 1 | Round out Doctor Movement | AC |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | 1 | Sutchers interact with patient | BL |  | 6 | 0 |  |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | 1 | Making Patient Body Interactive/Responsive to tools | BL |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | 1 | Scalpel interacts with patient | BL |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | 1 | Forcepts interact with patient | BL |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 1 | Event System Works with tools and patient. | ME |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | 1 | Recipes for event system | ME | ALL | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | 1 | Gauze interacts with patient | BL |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | 2 | Ui for recipies and events | ME | EA | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
52 | 2 | Anesthetic Machine Model | EA |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | 2 | Washing Station Model | EA |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | 2 | Refine Camera / perspective and only show tools and patient on patient camera | ALL |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | 1 | Heart rate more dynamic (changes speed and lets player know when the patinet is about to die) | EA | ME | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | 4 | Defibulator Model | EA |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
57 | 3 | Defibulator Functionality (Add more Functionality) **specify?? | EA |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
58 | 1 | Container dispensing container / system / method for Capsules | AC |  | 2.5 | 0 |  |  | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
59
36
61
62
63
64 |  | Backlog
65 | 4 | Fire Aesthetics | BL |  | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
66 | 3 | Fire Logic / Interaction | ME |  | 2 | 0 | 3 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67 | 3 | Moveable Gurney | EA |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 | 4 | Bear Model / class | EA |  | 5 | 5 |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
69 | 3 | Bear AI | EA |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | 3 | Bear Interacting with players | EA |  | 1 | 1 |  |  | 1 | bar: 2016-10-26 to 2016-12-12
55 | 5 | Refined player guidence (AI or some kind of tutoiral) | ME |  | 5 | 0 | 2 |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | 3 | alpha planning | ALL |  | 6 | 0 |  |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | 4 | Pull out stick from body | BL |  | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
58 | 4 | Pull out stick from body aesthetics |  |  | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
59 | 4 | Raccoons AI? --> stealing tools | BL |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | 4 | Raccoons Aesthetics | EA |  | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
77 | 3 | Pond (for collecting water in buckets) | AC |  | 1.5 | 1.5 |  |  | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
78 | 3 | Water bucket tool | AC |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | 3 | Add Dirty Hands Mechanic | AC | EA | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | 3 | Water Bucket Model | EA |  | 0.5 | 0 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | 3 | Highlight interactive element nearest to doctor | AC |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
82 | 4 | Prevent interactions with elements which are in range, but not in front of doctor |  |  | 0.5 | 0.5 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
| 2 | HeartBeat | ME |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | 1 | Fix highlighting for complex objects | AC |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | 1 | Add special highlighting to current necessery tool | AC |  | 1 | 1 |  |  | 1 | bar: 2016-10-26 to 2016-12-12
85 | 1 | Fx doctor colliders | AC |  | 0.25 | 0 |  |  | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 |  | Make/Update Doctor Prefab | AC |  | 0.25 | 0 |  |  | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 |  | Clean up project (remove defunct scripts / unused prefabs) | AC |  | 0.25 | 0 |  |  | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 |  | Aesthetics
89 |  | Patient body model Refinement | BL |  | 1 | 1 |  |  | 1 | bar: 2016-10-26 to 2016-12-12
90 |  | Refine Camera / perspective and only show tools and patient on patient camera
91 |  | Better wash Hands Meter | AC |  | 0.25 | 0.25 |  |  | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
92 |  | Fix Movement Bug | AC |  | 0.5 | 0 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Bascially fixed. Setting the mass of the doctors to ~0 means that any collision with another object will not generate that much force between them. With very little force, there is very little resulting change in volocity. You can still see the doctor move slightly when replicating this bug, but it is far better than it was before.
93 | 1 | Events for Bear, Fire, and Raccons | ME |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | 1 | Force canvas above doctor's head to "look at" the screen at all times. | AC |  | 0.75 | 0 |  |  | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | 1 | Graphics for Tools notifications | ME |  | 3 | 0 | 3 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
96 | 1 | Graphics for Environment event notifications | ME |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
97 | 1 | Graphics for button events | ME |  | 3 | 0 | 2 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | Attach graphics to event system | ME |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
98 | 1 | Set up button press graphics with Objects | ME |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
99 |  | Prevent tools from moving off surgery screen | AC |  | 1.5 | 0.5 |  |  | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
100 |  | Fix oringal tool matieral getting overwritten | AC
101 |  | Restrict players from leaving the area | BL |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
102 |  | Make arena bigger | BL |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
103 | 1 | New Tool Spawning when raccoons steal them | BL |  | 0.5 | 0 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
104 | 1 | Animal Spawning | BL |  | 0.5 | 0 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
105 | 1 | Icons over interactables | ME |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | Play testing Script | ALL |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0
| 1 | Put it together for alpha | ALL |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0
| 1 | Fail / Success | AC |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | Tutorial Slides | AC |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | Defibulator Cooldown
111 | 1 | Animate Heart Rate Monitor | ME |  | 6 | 0 |  |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 |  | Reported
112 | 1 | Incorporate Heart Rate Monitor | ME |  | 1 | 1 |  |  | 1 | [16 empty] | Reported | bar: 2016-10-26 to 2016-12-12
113 | 1 | Notifications for Bear and Wash hands | ME |  | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | Reported
114 | 1 | Make UI not screen dependent | ME |  | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | Reported
115 | [25 empty] | Reported
116 | [25 empty] | Reported
117 | [25 empty] | Reported
118 | [25 empty] | Reported
119 | [25 empty] | Reported
120 | [25 empty] | Reported
121 | [25 empty] | Reported
122 | [25 empty] | Reported
123 | [25 empty] | Reported
124 | [25 empty] | Reported
125 | [25 empty] | Reported
126 | [25 empty] | Reported
127 | [25 empty] | Reported
128 | [25 empty] | Reported
129 | [25 empty] | Reported
130 | [25 empty] | Reported
131 | [25 empty] | Reported
132 | [25 empty] | Reported
133 | [25 empty] | Reported
134 | [25 empty] | Reported
135 | [25 empty] | Reported
136 | [25 empty] | Reported
137 | [25 empty] | Reported
138 | [25 empty] | Reported
139 | [25 empty] | Reported
140 | [25 empty] | Reported
141 | [25 empty] | Reported
142 | [25 empty] | Reported
143 | [25 empty] | Reported
Bugs to be Fixed!!! | [24 empty] | Fix Description (if unusual or useful to later generations) | Status
107 | 1 | Fix floating tools off screen | AC |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reported
108 |  | make hands or something so tools don't float around in the world just on camera | [23 empty] | Reported
109 |  | Fix occassional sliding | AC |  | 0.25 | 0 |  |  | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reported
110 | 2 | Does fire generate multiple times in the same place? | ME |  | 0.5 | 0 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 |  | Reported
149 | 1 | Heart rate / Patient death last two states don't work right | ME |  | 0.5 | 0 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 |  | Reported
150 | 1 | Patient dies sometimes randomly (maybe when anesthetic machine runs out --> but not seemingly deterministically) | ME |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | Reported
151 | 1 | Can get stuck in fire, should you be able to walk through fire? | ME |  | 0.5 | 0.5 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | Reported
152 | 1 | Cant scare away bear | EA |  | 1 | 1 |  |  | 1 | [16 empty] | Reported | bar: 2016-10-26 to 2016-12-12
153 | 1 | Interactables too large sphere (causes the wrong things to be activted / too far away and bear not to work) | AC |  | 0.5 | 0.5 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | Reported
154 | [25 empty] | Reported
155 | [25 empty] | Reported
156 | [25 empty] | Reported
157 | [25 empty] | Reported
158 | [25 empty] | Reported
159 | [25 empty] | Reported
160 | [25 empty] | Reported
161 | [25 empty] | Reported
162 | [25 empty] | Reported
163 | [25 empty] | Reported
164 | [25 empty] | Reported
165 | [25 empty] | Reported
166 | [25 empty] | Reported
167 | [25 empty] | Reported
168 | [25 empty] | Reported
169 | [25 empty] | Reported
170 | [25 empty] | Reported
171 | [25 empty] | Reported
172 | [25 empty] | Reported
173 | [25 empty] | Reported
174 | [25 empty] | Reported
175 | [25 empty] | Reported
176 | [25 empty] | Reported
177 | [25 empty] | Reported
178 | [25 empty] | Reported
179 | [25 empty] | Reported
180 | [25 empty] | Reported
181 | [25 empty] | Reported
182 | [25 empty] | Reported
183 | [25 empty] | Reported
184 | [25 empty] | Reported
185 | [25 empty] | Reported
186 | [25 empty] | Reported
187 | [25 empty] | Reported
188 | [25 empty] | Reported
189 | [25 empty] | Reported
190 | [25 empty] | Reported
191 | [25 empty] | Reported
192 | [25 empty] | Reported
193 | [25 empty] | Reported
194 | [25 empty] | Reported
195 | [25 empty] | Reported
196 | [25 empty] | Reported
197 | [25 empty] | Reported
198 | [25 empty] | Reported
199 | [25 empty] | Reported
200 | [25 empty] | Reported
201 | [25 empty] | Reported
202 | [25 empty] | Reported
203 | [25 empty] | Reported
204 | [25 empty] | Reported
205 | [25 empty] | Reported
206 | [25 empty] | Reported
207
208
Interpreted Data
210 |  | Days | [6 empty] | 47 | 47 | 45 | 42 | 38 | 35 | 31 | 28 | 24 | 21 | 17 | 14 | 10 | 7 | 3 | 0
211 |  | Optimum | [5 empty] | Line | 189 | 189 | 180.9574 | 168.8936 | 152.8085 | 140.7447 | 124.6596 | 112.5957 | 96.5106 | 84.4468 | 68.3617 | 56.2979 | 40.2128 | 28.1489 | 12.0638 | 0
212
213 |  | Sum | [6 empty] | 189 | 189 | 189 | 189 | 189 | 189 | 189 | 189 | 189 | 189 | 189 | 189 | 189 | 189 | 0 | 0
214 |  | Rank (and not reduced to 0 after today)
215 |  | Rank 1 - The MOST important | 1 | [5 empty] | 116 | 116 | 115.5 | 112 | 95.5 | 89 | 83 | 49.75 | 45.25 | 41.5 | 21.5 | 15.5 | 9 | 8 | 8 | 8
216 |  |  | 2 | [5 empty] | 28.5 | 28.5 | 28.5 | 28.5 | 28.5 | 28.5 | 24.5 | 4.5 | 4.5 | 4.5 | 0.5 | 0 | 0 | 0 | 0 | 0
217 |  |  | 3 | [5 empty] | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 3.5 | 3.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5
218 |  |  | 4 | [5 empty] | 21.5 | 21.5 | 21.5 | 21.5 | 21.5 | 21.5 | 21.5 | 21.5 | 21.5 | 18.5 | 16.5 | 16.5 | 16.5 | 16.5 | 16.5 | 16.5
219 |  | Rank 5 - The LEAST important | 5 | [5 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
220
221 |  | Assigned (Replace these with your team members!)
222 |  | Morgan | ME |  |  |  |  | ME | 56 | 56 | 56 | 56 | 52.5 | 50.5 | 50.5 | 41.5 | 32.5 | 32.5 | 13.5 | 13 | 6.5 | 5.5 | 5.5 | 5.5
223 |  | Alex | AC |  |  |  |  | AC | 33.5 | 33.5 | 33.5 | 33.5 | 31 | 29.5 | 29.5 | 18.5 | 12.5 | 8.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75
224 |  | Eliana A | EA |  |  |  |  | EA | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 30.5 | 30.5 | 16.5 | 13 | 13 | 10 | 10 | 10 | 10 | 10 | 10
225 |  | Ben L | BL |  |  |  |  | BL | 29.5 | 29.5 | 29.5 | 29.5 | 26 | 26 | 26 | 13 | 13 | 10 | 9 | 9 | 7 | 7 | 7 | 7
226 |  | All | ALL |  |  |  |  | ALL | 40 | 40 | 39.5 | 36 | 29 | 29 | 19 | 12 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0
227 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
228 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
229 | [7 empty] | Unassigned | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5
230 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
231 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
232 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233
234
235 | [7 empty] | DateLine | 189 | 189 | 189 | 189 | 189 | 189 | 189 | 189 | 189 | 189 | 189 | 189 | 189 | 189 | 0 | 0
236

## Daily Scrum
Producer | 2016-12-05 |  | Team Members
Approved | Dates |  | Morgan | Alex | Eliana A | Ben L | All
| 2016-10-26 | Wed | PROJECT NOT STARTED YET | PROJECT NOT STARTED YET | PROJECT NOT STARTED YET | PROJECT NOT STARTED YET | PROJECT NOT STARTED YET
| 2016-10-27 | Thu | PROJECT NOT STARTED YET | PROJECT NOT STARTED YET | PROJECT NOT STARTED YET | PROJECT NOT STARTED YET | PROJECT NOT STARTED YET
| 2016-10-28 | Fri | Done: Met and planned the mechanics of the game Next: Meet with team, to refine game ideas Help: — | Done: Met and planned the mechanics of the game Next: Meet with team, to refine game ideas Help: — | Done: Met and planned the mechanics of the game Next: Meet with team, to refine game ideas Help: — | Done: Met and planned the mechanics of the game Next: Meet with team, to refine game ideas Help: — | Done: Met and planned the mechanics of the game Next: Find similar games, play them, and refine vision of game Help: —
| 2016-10-29 | Sat | Done: Met with team to refine game ideas Next: Continue Planning / refining game based on in-class advice Help: — | Done: Met with team to refine game ideas Next: Continue Planning / refining game based on in-class advice Help: — | Done: Met with team to refine game ideas Next: Continue Planning / refining game based on in-class advice Help: — | Done: Met with team to refine game ideas Next: Continue Planning / refining game based on in-class advice Help: — | Done: Organized notes on similar games, and refined vision for our game Next: Continue Planning / refining game Help: —
| 2016-10-30 | Sun | NA | NA | NA | NA | NA
| 2016-10-31 | Mon | NA | NA | NA | NA | NA
| 2016-11-01 | Tue | Done: Set up burndown chart, played Overcooked Next: Prepare the project to be worked on seperatly Help: — | Done: Set up burndown chart, played Overcooked Next: Prepare the project to be worked on seperatly Help: — | Done: Set up burndown chart, played Overcooked Next: Prepare the project to be worked on seperatly Help: — | Done: Set up burndown chart, played Overcooked Next: Prepare the project to be worked on seperatly Help: — | Done: Set up burndown chart, played Overcooked, and decided what we wanted to include in our game, what we wanted our game to add, and what we didn't want in our game Next: Plan what we need to see in our Prototype, add these to the burndown chart, and start working seperatly Help: —
| 2016-11-02 | Wed | Done: Set up API to enable parallel work between members Next: Camera Setup and SplitScreen Help: — | Done: Set up API to enable parallel work between members Next: Patient Placeholders and 4 doctors Help: — | Done: Set up API to enable parallel work between members Next: Layout basic level Help: — | Done: Set up API to enable parallel work between members Next: Controller Support Help: — | Done: Decided what we wanted to see in our Prototype, and set up a skeleton API for thouse features / divided burndown tasks Next: Come together to make the prototype deliverable Help: —
| 2016-11-03 | Thu | NA | NA | NA | NA | NA
| 2016-11-04 | Fri | Done: Set up Camera and Split Screen Next: Patient Vitals Help: — | NA | NA | NA | NA
| 2016-11-05 | Sat | NA | NA | Done: Next: Work on patient interaction with event system | NA | NA
| 2016-11-06 | Sun | Done: Patient Vitals and Fial State Next: Wait for advice during prototype deliverable and refine prject from there Help: — | Done: Doctors can use tools Next: Advice time. | Done: Patient Vitals Trigger events in state Next: Feedback from deliverable Help: — | Done: Controller support for up to four players. Buttons are set. A to pickup. X to interact. Win state in. Game controller skelly. Next: iterate game controls | Done: Integrated everyones code Next: Plan between now and the gold spike Help: --
| 2016-11-07 | Mon | NA | NA | NA | NA | Done: Planed between now and the goldspike Next: Play games / game research Help: NA
| 2016-11-08 | Tue | NA | NA | NA | NA | NA
| 2016-11-09 | Wed | NA | NA | NA | NA | NA
| 2016-11-10 | Thu | Done: Research for research and Analysis Document Next: Write Research and Analysis Help: -- |  | Done: Research for research and Analysis Document Next: Write Research and Analysis Help: -- |  | Done: Game research, talked about how they would effect our game Next: Come together and make game deliverable for GoldSpike Help: NA
| 2016-11-11 | Fri | Done: Research and Analysis Contribution Next: Implement Event System Help: -- |  | Done: Research and Analysis Contribution Next: Create all models for game. Make classes Help: -- |  | NA
| 2016-11-12 | Sat | Done: Event System Works with all tools and critical events Next: Heart rate better Help: -- |  | Done: Created scalpel, suture Next: All other models Help: -- |  | NA
| 2016-11-13 | Sun | Done: Heat rate better, and simple UI for displaying events Next: Prepare Project for Goldspike deliverable Help: -- |  | Done: Created a new animation for suturing, helped out members with other tasks Next: All other models Help: Do we need it? |  | Done: Put code together / final touches for GoldSpike as a group Next: Plan What we want for the aplha Help: --
| 2016-11-14 | Mon | NA |  | Done: Turned in Next: Feedback for class Help: -- |  | NA
| 2016-11-15 | Tue | NA |  | NA |  | NA
| 2016-11-16 | Wed | Done: Heart Beat has sound Next: Work on fire Help: -- |  |  |  | Done: Planed what we wanted for the alpha Next: -- Help: --
| 2016-11-17 | Thu | Done: Made fire prefabs and generable Next: Make graphics for notifications Help: -- |  |  |  | NA
| 2016-11-18 | Fri | Done: Started Graphics for Notification System Next: Finish Graphics for Notification System Help: -- |  |  |  | NA
| 2016-11-19 | Sat | Done: Finished Graphics for Notification System Next: Graphics for buttons hints Help: -- |  |  |  | NA
| 2016-11-20 | Sun | Done: Graphics for Buttons / hints Next: Connect Graphics to Event system Help: -- |  |  |  | NA
| 2016-11-21 | Mon | NA |  |  |  | NA
| 2016-11-22 | Tue | NA |  |  |  | NA
| 2016-11-23 | Wed | NA |  |  |  | NA
| 2016-11-24 | Thu | NA |  |  |  | NA
| 2016-11-25 | Fri | NA |  |  |  | NA
| 2016-11-26 | Sat | Done: Basic Debugging Next: Connect Graphis to event system Help: -- |  |  |  | NA
| 2016-11-27 | Sun | Done: Connected Graphics to event system and put together code with group Next: Help: -- |  |  |  | Done: Put together code for alpha deliverable and play testing script Next: Playtesting, and what do we need for the beta? Help: --
| 2016-11-28 | Mon
| 2016-11-29 | Tue
| 2016-11-30 | Wed
| 2016-12-01 | Thu
| 2016-12-02 | Fri
| 2016-12-03 | Sat
| 2016-12-04 | Sun
| 2016-12-05 | Mon
| 2016-12-06 | Tue
| 2016-12-07 | Wed
| 2016-12-08 | Thu